## Sheet1
Sun Shop Lookbook 2013 Live Date: 5/8/13 | http://mingle/projects/bcom_creative/cards/2079 | Producer: Josh Orlick Developer: Sarah Becker QA: Sonia Batra | http://www1.qa18creativebloomingdales.fds.com/shop/jewelry-accessories/all-sunglasses?id=4520
| DATE | QA STATUS | AFFECTED AREA | ISSUE | SCREEN SHOTS (2nd Sheet) Yes/No | REPORTED BY | DEVELOPER'S RESPONSE | PRODUCER notes
1 | 2013-05-01 | Open | Alt Text | The alt text for "The Sunglass Shop" is "Sunglass Shop 2013 Start". Should be "Sunglass Shop 2013" Alt text for "Ray-Ban", "Tom Ford", and "Kate Spade New York" do not have spaces in between each word. And "Ray-Ban" needs a dash in between the two words. | No | Sonia | Not in the original spec. COMPLETE by dev on 5/1.
2 | 2013-05-01 | Open | The Sunglass Shop link | The link does not click to anywhere. If the link is clicked, it should erase all the facets underneath the banner. | No | Sonia | Developer to change link as discussed. COMPLETED by dev on 5/2.
3 | 2013-05-01 | Open | The rollover transparent squares | The transparent squares when rolling over each category have a very thin line on the square that is not covering the full box. (see comp to match the transparent square when rolled over a category) | No | Sonia | RESOLVED: This is happening in IE 7 only. As per Joshua we can let it go.
4 | 2013-05-01 | Open | Rollover | When you hover onto a category and the transparent box appears, then you hover off of the banner the transparent box does not disappear | No | Sonia | COMPLETED by dev on 5/2
5 | 2013-05-01 | Open | Mouse icon | When you hover over a category, the hand icon does not appear | No | Sonia | RESOLVED: This is happening in IE 7 only. As per Joshua we can let it go.
6 | 2013-05-01 | Open | Shield | The URL for "Shield" category has an undefined parameter: http://www1.qa18creativebloomingdales.fds.com/shop/jewelry-accessories/undefined | No | Sonia | COMPLETED by dev on 5/2
7 | 2013-05-01 | Open | Cat Eye | The category browse page for "Cat Eye" does not show it's category banner: http://www1.qa18creativebloomingdales.fds.com/shop/jewelry-accessories/cat-eye?id=20024 | No | Sonia | Joshua to follow up; not for dev
8 | 2013-05-01 | Open | Category links | Some categories are taking you to browse pages, and 1 category "Polarized" is just filtering the search results underneath the banner. Which is the correct experience? Please make all consistent. | No | Sonia | Joshua forwarded link provided by Creative for "Polarized." COMPLETED by dev on 5/2.
9 | 2013-05-01 | Open | Coremetrics | The main links are not tagged. Please thrown an element tag when user clicks on one of the 6 options. Refer to the tagging document for additional clarification. The Kate Spade Link on the top nav is not tagged. | No | Charmi | COMPLETED by dev on 5/2
10 | 2013-05-01 | Open | Rollovers | Rollover texts needs to be black not grey | No | Jihye | COMPLETED by dev on 5/2
11
12
13
14
15
16
17
18
19
20
21
22
23